## Slide 1
August 4, 2016
Delaware’s State Innovation Model (SIM) Update

## Slide 2: Success in 2016: Critical path
1 July 2016 PT vendor report indicated 96 sites and 354 MDs, NPs, PAs; current Scorecard estimates 1,112 physicians, NPs, PAs in Delaware; adjusting for 10-20% part-time practitioners yields ~900-1,000 providers; does not include TCPI participants
2 Majority in Medicare Shared Savings Plans
Source: 2016 Medscape
Metrics
50% providers participating in practice transformation
Common Scorecard accessible to PCPs statewide
40% of Delawareans attributed to PCPs in value-based payment models
3 Healthy Neighborhoods launched
2
1
3
4
Status
  West/Central Sussex launched July 21
  HN project director continuing conversations in wave 1 HNs
  ~20% Delawareans in value-based payment models2
  Payers continuing to enroll practices
  ~35-40% providers enrolled1
  Developing plan to reach additional providers
  V2.0 accessible to 21 testing practices
  Scorecard enrollment, provider webinars live
  On track for September statewide release

## Slide 3: Success in 2016: Supporting innovations
Metrics
Workforce curriculum available
Behavioral health integration testing program launched
Health literacy materials launched on website
APCD on path to be operational in 2017
2
1
3
4
Status
  DCHI published position paper on multi-payer access to claims
  Governor signed legislation enabling APCD on July 21
  Not launched
  ab+c developing content on www.choosehealthde.com
  Not available
  Vendors beginning curriculum development; intend to launch first module in October
  Not launched
  Implementation plan to be shared at August DCHI Board meeting for approval; plan to launch in Fall

## Slide 4: Success in 2016: DCHI Operational sustainability
Metrics
Staff hired for administration, Healthy Neighborhoods, Clinical Committees
Broad base of financial contributors
DCHI program dashboard live
2
1
3
Status
  Dashboard with initial draft of measures to be shared at August DCHI Board meeting
  Executive Assistant and Healthy Neighborhoods project director hired
  Recruitment underway for HN Program Manager and Community Coordinators
  Board Strategic Financial Planning meeting held in July
  Plan to continue strategic planning discussions

## Slide 5: West/Central Sussex Local Council is the first Healthy Neighborhood
  DCHI launched its first Healthy Neighborhood in West/Central Sussex on July 21
  West/Central Sussex includes ~10% of Delaware’s population and covers a large geographic area
  There is a high need in the Neighborhood, as many health indicators and social determinants of health are lower than US average and, in some cases, even lower than Delaware average
  West/Central Sussex has a strong infrastructure of community engagement (e.g., Sussex County Health Coalition and Healthier Sussex County). The Healthy Neighborhood approach provides robust representation from the community including residents, community organizations, employers and health systems

## Slide 6: DCHI draft consensus paper, “Licensing and Credentialing Health Care Providers”
Coordinated, statewide efforts are needed to reduce and eliminate providers' barriers to delivering care. The Workforce and Education Committee has identified the burdensome processes of credentialing as a key area for improving provider workflow.
Recommendations
  Identify the end goal for streamlined credentialing procedures within Delaware
  Operationally define and set parameters related to applications, time limits
  State legislation should be considered as a policy lever to set streamlined credentialing parameters for hospitals, provider networks, and payers
  Delaware should transition to an Automated Credentialing System in the future
  Ensure providers new to Delaware have access to licensing and credentialing resources
  Remove the Delaware Practical Board Examination as a requirement for dental licensure

## Slide 7
Upcoming DCHI Committee Meetings
  Please check the DCHI website (www.DEhealthinnovation.org) for the latest information about all DCHI Board and Committee meetings
  Aug 11, 1:00pm
  UD STAR Campus
Workforce and Education
  Aug 17, 1:00pm
  UD STAR Campus
Healthy Neighborhoods
  Aug 16, 1:00pm
  UD STAR Campus
Clinical
  Aug 10, 4:30pm
  UD STAR Campus
Payment Model Monitoring
  Aug 4, 1:00pm
  Edgehill Shopping Ctr
Patient and Consumer Advisory