## DEFAC Timeline
Delaware Health Care Spending and Quality Benchmarks Timeline 2019-2023
The purpose of this document is to identify when a) DEFAC and DHCC need to take key action steps and b) needed data are expected to be available.
Legend
| March | April | May | June | July | August | September | October | November | December | January | February
Setting the Spending Benchmark - DEFAC
Annual review of the components of PGSP for the following calendar year | bar: April
Report changes, if any, by May 31 of the year prior to Governor and DHCC | bar: May
Announce spending benchmark for following calendar year by July 1 | bar: July

## DHCC Spending B'mark Timeline
Delaware Health Care Spending and Quality Benchmarks Timeline 2019-2023
Legend
Work to be performed by DHCC for Spending Benchmark
Work to be performed by DMMA for Spending Benchmark
Work to be performed by commercial insurers, Medicaid MCOs, Medicare and Medicare MCOs for Spending Benchmark
Performance Assessment of Spending Benchmark - DHCC | March | April | May | June | July | August | September | October | November | December | January | February
DHCC to update website with file submission instructions | bar: May to June
DHCC-hosted All-Insurer Briefing to discuss TME reporting requirements | bar: May to June
DHCC meeting with DMMA to discuss TME reporting requirements | bar: June to July
DHCC request of CMS for Medicare FFS data | bar: June
DHCC pulls VA data | bar: July
TME and MLR reports from insurers due | bar: August
DHCC conducts insurer TME data validation and follow-up | bar: August to September
TME data from DMMA due | bar: September
TME data from Medicare due | bar: September
DHCC calculates performance against the Benchmark and prepares publishable analysis | bar: September to November
DHCC releases reports | bar: November to December

## DHCC Qual B'Mark Timeline
Delaware Health Care Spending and Quality Benchmarks Timeline 2019-2023
Legend
Work to be performed by DHCC for Quality Benchmarks
Work to be performed by NCQA for Quality Benchmarks
Work to be performed by health insurers for Quality Benchmarks
Performance Assessment of Quality Benchmark - DHCC | March | April | May | June | July | August | September | October | November | December | January | February
Set Concurrent Use of Opioids and Benzodiazepines Benchmark 2019 only
Request data from health insurers to create benchmark - March 31, 2019 | March: 2019 only
Receive data from health insurers - August 1, 2019 | August: 2019 only
Measure and Publish Performance Against the Benchmarks 2019-2021
DHCC to update website with file submission instructions | bar: May to June
Request the Emergency Department Utilization national observed rate from NCQA - March 31 | bar: March
Request health insurers submit performance data - March 31 | bar: March
Receive the Emergency Department Utilization national observed rate from NCQA - August 1 | bar: August
Receive performance data from health insurers - August 1 | bar: August
Calculate performance for all measures except for Opioid-Related Overdose Deaths - September 30 | bar: September
Publish performance data for all measures except for Opioid-Related Overdose Deaths - early November | bar: November
Calculate performance for Opioid-Related Overdose Deaths for the performance period two calendar years prior - February 1 | bar: February
Update published performance data to include Opioid-Related Overdose Deaths - February 28 | bar: February
Update Benchmarks 2021 -2023
Commence review of the benchmark measures and methodology to define quality benchmarks for the year beginning 2022 - early January 2021 | bar: January
Complete review of the benchmark measures and methodology to define quality benchmarks for the year beginning 2022 - September 30, 2021 | bar: September